## WBS_actual
Work Breakdown Structure | [7 empty] | Name of Project
© 2017 by Vertex42.com
| Project Start | 2021-07-01 | [6 empty] | Work Breakdown Structure
Level | WBS | Task Description | Description | Primary Assignee | Secondary Assignee | Start | End | Notes
1 | 1 | IHUBDB-843 | [6 empty] | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Task Level 2 description | Reference Data Ingestion |  |  | 2021-07-01 | 2021-09-17 | 21 tables
2 | 1.2 | Task Level 2 Description | POC / SIT | Jason | Cecilia |  |  | Q3 commit
3 | 1.2.1 | Task Level 3 Description | Data Analysis - understand requirement | Jason | Cecilia |  |  | Q3 timeline 9.24
3 | 1.2.2 | Task Level 3 Description | SIT test | Jason | Cecilia |  |  | MMM / Mortgage Securitisation
4 | 1.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available | Jason | Cecilia
5 | 1.2.2.1.1 | Task Level 5 Description | Check source location/ ingestion methods ( who trigger juniper) | Jason | Cecilia
4 | 1.2.2.2 | Task Level 4 Description | contact with Source team, make sure resource available | Jason | Cecilia |  |  | No RDL
4 | 1.2.2.3 | Task Level 4 Description | POC Juniper upload a file to GCP DEV | Jason | Cecilia |  |  | go to Production Server
4 | 1.2.2.4 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 1.2.2.5 | Task Level 4 Description | Juniper upload files in schedule to GCP Production Server DEV | Jason | Cecilia
4 | 1.2.2.6 | Task Level 4 Description | Data Testing | Jason | Cecilia
4 | 1.2.2.7 | Task Level 4 Description | UAT sign-off | Jason | Cecilia
4 | 1.2.2.8 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end | Jason | Cecilia
2 | 1.3 | Task Level 2 Description |  | Arnan
4 | 1.3.1.1 | Task Level 4 Description | Prepare release | Jason | Cecilia
4 | 1.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 1.3.1.3 | Task Level 4 Description | release | Jason | Cecilia
4 | 1.3.1.4 | Task Level 4 Description | Health check | Jason | Cecilia
1 | 2 | IHUBDB-233
2 | 2.1 | Task Level 2 description | BG Data Ingestion |  |  | 2021-07-01 | 2021-09-17 | 10 tables
2 | 2.2 | Task Level 2 Description | POC / SIT | Young |  |  |  | Q3 commit
3 | 2.2.1 | Task Level 3 Description | Data Analysis - understand requirement | Young |  |  |  | Q3 timeline 9.24
3 | 2.2.2 | Task Level 3 Description | SIT test | Young |  |  |  | Only Dev for Q3
4 | 2.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available | Young |  |  |  | MMM
5 | 2.2.2.1.1 | Task Level 5 Description | Check source location/ ingestion methods ( who trigger juniper) | Young
4 | 2.2.2.2 | Task Level 4 Description | contact with Source team, make sure resource available | Young
4 | 2.2.2.3 | Task Level 4 Description | POC Juniper upload a file to GCP DEV ( copy book + data) | Young
4 | 2.2.2.4 | Task Level 4 Description | spin up vm, run python/java program to convert into BG table | Arnan
4 | 2.2.2.5 | Task Level 4 Description | Juniper upload files in schedule to GCP DEV | Young
4 | 2.2.2.6 | Task Level 4 Description | spin up vm, run python/java program to convert files into BG table | Arnan
4 | 2.2.2.7 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 2.2.2.8 | Task Level 4 Description | Data Testing | Young
4 | 2.2.2.9 | Task Level 4 Description | UAT sign-off | Young
4 | 2.2.2.10 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end | Young
2 | 2.3 | Task Level 2 Description
4 | 2.3.1.1 | Task Level 4 Description | Prepare release | Young |  |  |  | No production for Q3
4 | 2.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 2.3.1.3 | Task Level 4 Description | release | Young
4 | 2.3.1.4 | Task Level 4 Description | Health check | Young
1 | 3 | IHUBDB-227
2 | 3.1 | Task Level 2 Data Ingestion | RALF Data Ingestion |  |  | 2021-07-01 | 2021-09-17 | 22 tables
2 | 3.2 | Task Level 2 Description | POC / SIT | Cecilia | Jason |  |  | Q3 commit
3 | 3.2.1 | Task Level 3 Description | Data Analysis - understand requirement | Cecilia | Jason |  |  | Q3 timeline 9.24
3 | 3.2.2 | Task Level 3 Description | SIT test | Cecilia | Jason |  |  | MMM
4 | 3.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available | Cecilia | Jason |  |  | production
5 | 3.2.2.1.1 | Task Level 5 Description | Check source location/ ingestion methods ( who trigger juniper) | Cecilia | Jason
5 | 3.2.2.1.2 | Task Level 5 Description | What is the timeline for RALF | Cecilia | Jason
4 | 3.2.2.2 | Task Level 4 Description | POC Juniper upload a file to GCP DEV | Cecilia | Jason
4 | 3.2.2.3 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 3.2.2.4 | Task Level 4 Description | Juniper upload files in schedule to GCP DEV | Cecilia | Jason
4 | 3.2.2.5 | Task Level 4 Description | Data Testing | Cecilia | Jason
4 | 3.2.2.6 | Task Level 4 Description | UAT sign-off | Cecilia | Jason
4 | 3.2.2.7 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end | Cecilia | Jason
2 | 3.3 | Task Level 2 Description
4 | 3.3.1.1 | Task Level 4 Description | Prepare release | Cecilia | Jason
4 | 3.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 3.3.1.3 | Task Level 4 Description | release | Cecilia | Jason
4 | 3.3.1.4 | Task Level 4 Description | Health check | Cecilia | Jason
1 | 4 | IHUBDB-226 | [6 empty] | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 4.1 | Task Level 2 Refrence Data Ingestion | OSCAR Data Ingestion |  |  | 2021-07-01 | 2021-09-17 | 7 tables
2 | 4.2 | Task Level 2 Description | POC / SIT | Young | Leon |  |  | Q3 commit
3 | 4.2.1 | Task Level 3 Description | Data Analysis - understand requirement | Young | Leon |  |  | Q3 timeline 9.24
3 | 4.2.2 | Task Level 3 Description | SIT test | Young | Leon |  |  | MMM / Mortgage Securitisation
4 | 4.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available | Young | Leon |  |  | production
4 | 4.2.2.2 | Task Level 4 Description | POC Juniper upload a file to GCP DEV | Young | Leon
4 | 4.2.2.3 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 4.2.2.4 | Task Level 4 Description | Juniper upload files in schedule to GCP DEV | Young | Leon
4 | 4.2.2.5 | Task Level 4 Description | Data Testing | Young | Leon
4 | 4.2.2.6 | Task Level 4 Description | UAT sign-off | Young | Leon
4 | 4.2.2.7 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end | Young | Leon
2 | 4.3 | Task Level 2 Description
4 | 4.3.1.1 | Task Level 4 Description | Prepare release | Young | Leon
4 | 4.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view | Arnan
4 | 4.3.1.3 | Task Level 4 Description | release | Young | Leon
4 | 4.3.1.4 | Task Level 4 Description | Health check | Young | Leon
1 | 5 | IHUBDB-235
2 | 5.1 | Task Level 2 Refrence Data Ingestion | AOL Data Ingestion | Leon | Young | 2021-07-01 | 2021-09-17 | 50/108 tables
2 | 5.2 | Task Level 2 Description | POC / SIT | Leon | Young |  |  | Q3 commit
3 | 5.2.1 | Task Level 3 Description | Data Analysis - understand requirement | Leon | Young |  |  | Q3 timeline 9.24
3 | 5.2.2 | Task Level 3 Description | SIT test | Leon | Young |  |  | production
4 | 5.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available
4 | 5.2.2.2 | Task Level 4 Description | POC Juniper upload a file to GCP DEV ( copy book + data) | Leon | Young
4 | 5.2.2.3 | Task Level 4 Description | spin up vm, run python/java program to convert into BG table
4 | 5.2.2.4 | Task Level 4 Description | Juniper upload files in schedule to GCP DEV | Leon | Young
4 | 5.2.2.5 | Task Level 4 Description | spin up vm, run python/java program to convert files into BG table
4 | 5.2.2.6 | Task Level 4 Description | GCP dataset,schema checking, authrozie view
4 | 5.2.2.7 | Task Level 4 Description | Data Testing | Leon | Young
4 | 5.2.2.8 | Task Level 4 Description | UAT sign-off | Leon | Young
4 | 5.2.2.9 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end | Leon | Young
2 | 5.3 | Task Level 2 Description
4 | 5.3.1.1 | Task Level 4 Description | Prepare release | Leon | Young
4 | 5.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view
4 | 5.3.1.3 | Task Level 4 Description | release | Leon | Young
4 | 5.3.1.4 | Task Level 4 Description | Health check | Leon | Young
1 | 6 | IHUBDB-1200
2 | 6.1 | Task Level 2 Refrence Data Ingestion | Reporting |  |  | 2021-07-01 | 2021-09-17 | 5/13 reports
2 | 6.2 | Task Level 2 Description | POC / SIT |  |  |  |  | Q3 commit
3 | 6.2.1 | Task Level 3 Description | Data Analysis - understand requirement |  |  |  |  | Q3 timeline 9.24
3 | 6.2.2 | Task Level 3 Description | SIT test |  |  |  |  | Mortgage Securitisation
4 | 6.2.2.1 | Task Level 4 Description | contact with Source team, make sure resource available |  |  |  |  | Only Dev for Q3
4 | 6.2.2.2 | Task Level 4 Description | POC Juniper upload a file to GCP DEV
4 | 6.2.2.3 | Task Level 4 Description | GCP dataset,schema checking, authrozie view |  |  | Arnan
4 | 6.2.2.4 | Task Level 4 Description | Juniper upload files in schedule to GCP DEV
4 | 6.2.2.5 | Task Level 4 Description | Data Testing
4 | 6.2.2.6 | Task Level 4 Description | UAT sign-off
4 | 6.2.2.7 | Task Level 4 Description | wirte documents in confluence page for whole end 2 end
2 | 6.3 | Task Level 2 Description
4 | 6.3.1.1 | Task Level 4 Description | Prepare release
4 | 6.3.1.2 | Task Level 4 Description | GCP dataset,schema checking, authrozie view |  |  | Arnan
4 | 6.3.1.3 | Task Level 4 Description | release
4 | 6.3.1.4 | Task Level 4 Description | Health check

## WBS
Work Breakdown Structure | [5 empty] | Name of Project
© 2017 by Vertex42.com
| Project Start | 2017-01-02 |  |  |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1 |  |  |  |  | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Task Level 2 Description
2 | 1.2 | Task Level 2 Description
3 | 1.2.1 | Task Level 3 Description
3 | 1.2.2 | Task Level 3 Description
4 | 1.2.2.1 | Task Level 4 Description
4 | 1.2.2.2 | Task Level 4 Description
4 | 1.2.2.3 | Task Level 4 Description
2 | 1.3 | Task Level 2 Description
1 | 2 | Phase 2
2 | 2.1 | Task Level 2 Description
3 | 2.1.1 | Task Level 3 Description
3 | 2.1.2 | Task Level 3 Description
1 | 3 | Phase 3
2 | 3.1 | Task Level 2 Description
3 | 3.1.1 | Task Level 3 Description
4 | 3.1.1.1 | Task Level 4 Description
2 | 3.2 | Task Level 2 Description
◄ Add new rows ABOVE this one.

## Help
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.