## Version
|  | Weekly Status Report |  |  | Version 1.6
修订历史
版本号 | 版本发布日期 | 作者 | Reviewer | Approver | Content
1 | 2016-03-07 | Lakkie | PMO | Alan | Initial Release.
1.1 |  | Lakkie | PMO | Alan
1.2 |  | Lakkie | PMO | Alan
1.3 |  | Lakkie | PMO | Alan
1.4 |  | Lakkie | PMO | Alan
1.5 | 2016-10-20 | Lakkie | PMO | Alan | Add Earned Value Analysis for calculating project Phases Schedule.
1.6 | 2016-11-23 | Sherry | PMO | Alan | 1, Added the variance status monitoring(<5%-Green, 5%~15% Amber, >15% Red) 2, Added the Recource plan 3, Remove the Summary Overview of this week 4, The task progress will be either 100% or 0%
包含在本文档的任何信息不能用于Pactera创建本文档目的之外的任何目的，未经Pactera的书面授权，本文档(整体或部分)也不能被复制或发表。
文思海辉机密

## Plan V1.0
Type | Item | Module | Effort (MD) | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
|  |  |  | HC | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD (TL) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD(SSE) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD(SE) | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Date | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13
Non-functional | Development Environment Setup |  | 12 |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Extract Sample Xml |  | 33 |  | 0 | 6 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Parameterize Xml Message |  | 35 |  | 0 | 0 | 0 | 3 | 12 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | XML Message Template Mainatance |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Test XML Messager Generation |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Test XML Message Publish |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Operation Logging |  | 32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Non-functional | Post Implementation Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
| Total Efforts (MD) |  | 217 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dedicated Project Team Structure | Level | Efforts (HM) | Apr | Dec | Jan | Feb | Mar | Apr
|  | TBD (TL) | 4.1
|  | TBD (SSE) | 3.64
|  | TBD (SE) | 2.5
Total Effort (HM)

## Plan V1.1
Type | Item | Module | Effort (MD) | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
|  |  |  | HC | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD (TL) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD(SSE) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TBD(SE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Date | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13
Non-functional | Development Environment Setup |  | 12 |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Extract Sample Xml |  | 33 |  | 0 | 6 | 10 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Parameterize Xml Message |  | 35 |  | 0 | 0 | 0 | 0 | 1 | 10 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | XML Message Template Mainatance |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Test XML Messager Generation |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 15 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Test XML Message Publish |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Functional | Operation Logging |  | 32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | -3
Non-functional | Post Implementation Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
| Total Efforts (MD) |  | 217 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dedicated Project Team Structure | Level | Efforts (HM) | Apr | Dec | Jan | Feb | Mar | Apr
|  | TBD (TL) | 4.1
|  | TBD (SSE) | 3.64
|  | TBD (SE) | 2.5
Total Effort (HM)

## W1
Project Weekly Status Report (6May - 10May,2019)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | HSBC 2021 TREATS Source Code QC tools |  | Report Date | 2021-03-01
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Accumulated deviation | Prediction on the Accumulated deviation of Next week | Cause Analysis of Deviation& Response measures
Schedule |  |  | 0%
Effort | 75 | 71 | 4 | 0% | 0%
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 75% | Yellow | 2021-03-30
Phase 3 OTX tasks | 75% | Yellow | 2021-03-30
Phase 4 ICCM & OTX tasks | 40% |  | 2021-04-30
Phase 5 ICCM & OTX tasks | 0% |  | 2021-06-30
Phase 6 ICCM & OTX tasks | 0% |  | 2021-08-30
Post Implementation Support | 0% | Green | 2021-07-15
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
1 | ICCM project development | 2021-02-22 | 2021-02-26 | 100% | Alex H P XIE
2 | OTX project development | 2021-02-22 | 2021-02-26 | 100% | Min Z QIU, Kashing
3 | Interview | 2021-02-22 | 2021-02-26 | 100% | Wesley
4
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions |  | Current Status | Expected Mitigation Date
1 | some projects schedule always change |  | low
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | The onboard process is slow and pending on HSBC side, ICCM team not have enough resource to handle more projects |  | Medium
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Remark
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A34: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A35: Catherine: From Risk& Issue Manangement form
Note on D35: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A41: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A46: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W2
Project Weekly Status Report (1Mar - 5Mar,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-03-08
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Accumulated deviation | Prediction on the Accumulated deviation of Next week | Cause Analysis of Deviation& Response measures
Schedule |  |  | 0%
Effort | 90 | 75 | 15 | 0% | 0%
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 75% | Yellow | 2021-03-30 |  | 部分项目由于需求方问题延期做release，开发基本完成
Phase 3 OTX tasks | 75% | Yellow | 2021-03-30 |  | 部分项目由于需求方问题延期做release，开发基本完成
Phase 4 ICCM & OTX tasks | 40% |  | 2021-04-30
Phase 5 ICCM & OTX tasks | 5% |  | 2021-06-30
Phase 6 ICCM & OTX tasks | 0% |  | 2021-08-30
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-03-08 | 2021-03-12 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-03-08 | 2021-03-12 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 100% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-03-08 | 2021-03-12 | 0% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-03-08 | 2021-03-12 | 0% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 0% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 0% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions |  | Current Status | Expected Mitigation Date
1 | 部分于原定onboard人员由于汇丰系统原因已经推迟了大半个月入职。目前的影响除了任务的进度会比计划上延缓，还有就是部分等待入职的人员产生了不满，有一定风险放弃入职 |  | High | 1. 更新项目的计划，并通知汇丰对接Pod leader相应情况。 2.让交付助理和PTA同事向pending入职同事解释清楚情况并安抚，对于部分高风险放弃入职人员提前一点在场外入职，先让这些同事了解项目的基本情况，或者协助公司做一些事情。 |  | Open | 2021-03-14
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Open | 项目经理和leader | 2021-03-29
2 | 一些项目由于提需求方的各种原因延期比较严重，导致我们的同事工作计划被打乱，一些项目不能按计划close。 |  | 低 | 主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 | Open | 对应的项目负责人 | 2021-03-29
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Remark
曾泽理 | 2021-03-15 | TBC |  |  | developer
梁世杰 | 2021-03-15 | TBC |  |  | developer
胡霞波 | 2021-03-15 | TBC |  |  | PM,下周三在场外入职
黄颖钧 | 2021-03-22 | TBC |  |  | BA
张颖 | 2021-03-29 | TBC |  |  | developer
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A34: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A35: Catherine: From Risk& Issue Manangement form
Note on D35: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A41: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A46: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W3
Project Weekly Status Report (8Mar - 12Mar,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-03-15
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Accumulated deviation | Prediction on the Accumulated deviation of Next week | Cause Analysis of Deviation& Response measures
Schedule |  |  | 0%
Effort | 75 | 75 | 0 | 0% | 0%
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 82% | Yellow | 2021-03-30 |  | 部分项目由于需求方问题延期做release，开发基本完成
Phase 3 OTX tasks | 82% | Yellow | 2021-03-30 |  | 部分项目由于需求方问题延期做release，开发基本完成
Phase 4 ICCM & OTX tasks | 45% |  | 2021-04-30
Phase 5 ICCM & OTX tasks | 8% |  | 2021-06-30
Phase 6 ICCM & OTX tasks | 0% |  | 2021-08-30
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-03-08 | 2021-03-12 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-03-08 | 2021-03-12 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 100% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-03-08 | 2021-03-12 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-03-15 | 2021-03-19 | 0% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-03-15 | 2021-03-19 | 0% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-03-15 | 2021-03-19 | 0% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-03-15 | 2021-03-19 | 0% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions |  | Current Status | Expected Mitigation Date
1 | 部分于原定onboard人员由于汇丰系统原因已经推迟了大半个月入职。目前的影响除了任务的进度会比计划上延缓，还有就是部分等待入职的人员产生了不满，有一定风险放弃入职 |  | High | 1. 更新项目的计划，并通知汇丰对接Pod leader相应情况。 2.让交付助理和PTA同事向pending入职同事解释清楚情况并安抚，对于部分高风险放弃入职人员提前一点在场外入职，先让这些同事了解项目的基本情况，或者协助公司做一些事情。 |  | Open | 2021-03-22
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Open | 项目经理和leader | 2021-03-29
2 | 一些项目由于提需求方的各种原因延期比较严重，导致我们的同事工作计划被打乱，一些项目不能按计划close。 |  | 低 | 主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 | Open | 对应的项目负责人 | 2021-03-29
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Remark
曾泽理 | 2021-03-22 | TBC |  |  | developer（上周开始on bench）
梁世杰 | 2021-03-22 | TBC |  |  | developer（上周开始on bench）
胡霞波 | 2021-03-22 | TBC |  |  | PM（上周开始on bench）
黄颖钧 | 2021-03-22 | TBC |  |  | BA
张颖 | 2021-03-29 | TBC |  |  | developer
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A34: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A35: Catherine: From Risk& Issue Manangement form
Note on D35: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A41: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A46: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W6
Project Weekly Status Report (8Mar - 12Mar,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-03-15
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Accumulated deviation | Prediction on the Accumulated deviation of Next week | Cause Analysis of Deviation& Response measures
Schedule | 67% | 67% | 0%
Effort | 100 | 100 | 0 | 0% | 0%
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 60% | Yellow | 2021-04-30
Phase 5 ICCM & OTX tasks | 20% | Yellow | 2021-06-30
Phase 6 ICCM & OTX tasks | 0% | Yellow | 2021-08-30
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-04-06 | 2021-04-09 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-06 | 2021-04-09 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-04-06 | 2021-04-09 | 100% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-04-06 | 2021-04-09 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-04-12 | 2021-04-16 | 0% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-12 | 2021-04-16 | 0% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-04-12 | 2021-04-16 | 0% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-04-12 | 2021-04-16 | 0% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions |  | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | High | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Open | 2021-04-30
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Open | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Remark
曾泽理 | 2021-03-22 | 2021-03-22 |  |  | developer
梁世杰 | 2021-03-22 | 2021-03-22 |  |  | developer
胡霞波 | 2021-03-22 | 2021-03-22 |  |  | PM
黄颖钧 | 2021-03-22 | 2021-03-22 |  |  | BA
张颖 | 2021-03-29 | 2021-03-29 |  |  | developer
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A34: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A35: Catherine: From Risk& Issue Manangement form
Note on D35: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A41: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A46: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W7
Project Weekly Status Report (8Mar - 12Mar,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-03-15
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Accumulated deviation | Prediction on the Accumulated deviation of Next week | Cause Analysis of Deviation& Response measures
Schedule | 67% | 67% | 0%
Effort | 100 | 100 | 0 | 0% | 0%
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 60% | Yellow | 2021-04-30
Phase 5 ICCM & OTX tasks | 20% | Yellow | 2021-06-30
Phase 6 ICCM & OTX tasks | 0% | Yellow | 2021-08-30
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-04-06 | 2021-04-09 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-06 | 2021-04-09 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 3 SIT/UAT/Release | 2021-04-06 | 2021-04-09 | 100% | Alex H P XIE
4 | OTX project development Phase 3 SIT/UAT/Release | 2021-04-06 | 2021-04-09 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-04-12 | 2021-04-16 | 0% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-12 | 2021-04-16 | 0% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-04-12 | 2021-04-16 | 0% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-04-12 | 2021-04-16 | 0% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions |  | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | High | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Open | 2021-04-30
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Open | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Remark
曾泽理 | 2021-03-22 | 2021-03-22 |  |  | developer
梁世杰 | 2021-03-22 | 2021-03-22 |  |  | developer
胡霞波 | 2021-03-22 | 2021-03-22 |  |  | PM
黄颖钧 | 2021-03-22 | 2021-03-22 |  |  | BA
张颖 | 2021-03-29 | 2021-03-29 |  |  | developer
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A34: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A35: Catherine: From Risk& Issue Manangement form
Note on D35: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A41: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A46: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W8
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-04-25
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 70% | 70% | 0% | 72% | 2%
Effort | 15 | 15 | 0 | 25 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 70% | Yellow | 2021-04-30
Phase 5 ICCM & OTX tasks | 35% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 5% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-04-19 | 2021-04-23 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-19 | 2021-04-23 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-04-19 | 2021-04-23 | 100% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-04-19 | 2021-04-23 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-04-26 | 2021-04-30 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-04-26 | 2021-04-30 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-04-26 | 2021-04-30 | 100% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-04-26 | 2021-05-14 | 100% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Open | 2021-04-30
2 | 五月可能会比较少porject进来，未必能接到计划中的项目分值 |  | Medium | 已和BOS沟通，假如新的项目数不够，各个汇丰的Pod会hand over部分项目给我们 |  | Open | 2021-05-20
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 | 2021-03-22 | 2021-03-22 |  |  | low
梁世杰 | 2021-03-22 | 2021-03-22 |  |  | low
胡霞波 | 2021-03-22 | 2021-03-22 |  |  | low
黄颖钧 | 2021-03-22 | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | low
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | medium
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
杨志恒 |  | 2020-07-02 |  |  | low
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 | 2021-03-29 | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A39: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A44: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W10
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-05-07
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 73% | 73% | 0% | 75% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 75% | Green | 2021-04-30
Phase 5 ICCM & OTX tasks | 37% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 6% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-05-03 | 2021-05-07 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-05-03 | 2021-05-07 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-03 | 2021-05-07 | 100% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-03 | 2021-05-07 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project development Phase 4 | 2021-05-10 | 2021-05-14 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-05-10 | 2021-05-14 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-10 | 2021-05-14 | 100% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-10 | 2021-05-14 | 100% | Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月可能会比较少porject进来，未必能接到计划中的项目分值 |  | Medium | 已和BOS沟通，假如新的项目数不够，各个汇丰的Pod会hand over部分项目给我们 |  | Open | 2021-05-20
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | low
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
杨志恒 |  | 2020-07-02 |  |  | high | Planned last day 28-May
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A39: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A44: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W11
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | Wesley |  | Reviewed by | PMO |  | Confirmed by | Alan
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-05-16
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 75% | 75% | 0% | 77% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 95% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 48% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 10% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-05-10 | 2021-05-14 | 100% | Alex H P XIE
2 | OTX project development Phase 4 | 2021-05-10 | 2021-05-14 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-10 | 2021-05-14 | 100% | Alex H P XIE
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-10 | 2021-05-14 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-05-17 | 2021-05-21 | 100% | Alex H P XIE
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-05-17 | 2021-05-21 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-05-17 | 2021-05-21 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-05-17 | 2021-05-21 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月可能会比较少porject进来，未必能接到计划中的项目分值 |  | Medium | 已和BOS沟通，假如新的项目数不够，各个汇丰的Pod会hand over部分项目给我们 |  | Open | 2021-05-20
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
杨志恒 |  | 2020-07-02 |  |  | high | Planned last day 28-May
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A39: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A44: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W12
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | hubo |  | Reviewed by | PMO |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-05-22
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 77% | 77% | 0% | 79% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 58% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 17% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-05-17 | 2021-05-21 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-05-17 | 2021-05-21 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-17 | 2021-05-21 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-17 | 2021-05-21 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-05-24 | 2021-05-28 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-05-24 | 2021-05-28 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-05-24 | 2021-05-28 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-05-24 | 2021-05-28 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月可能会比较少porject进来，未必能接到计划中的项目分值 |  | Medium | 已和BOS沟通，假如新的项目数不够，各个汇丰的Pod会hand over部分项目给我们 |  | Open | 2021-05-20
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。 |  | 中 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
杨志恒 |  | 2020-07-02 |  |  | high | Planned last day 28-May
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A39: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A44: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W13
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | hubo |  | Reviewed by | PMO |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-05-28
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 79% | 79% | 0% | 81% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 65% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 19% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-05-24 | 2021-05-28 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-05-24 | 2021-05-28 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-24 | 2021-05-28 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-24 | 2021-05-28 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-05-31 | 2021-06-04 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-05-31 | 2021-06-04 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-05-31 | 2021-06-04 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-05-31 | 2021-06-04 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月、六月同步进行的project相对集中。部分项目时间需错峰调整 |  | Medium | 与客户及内部同事沟通，部分能错峰的，做好排期优化调整 |  | Open | 2021-05-28
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。（OTX部分交接任务分担及ICCM部分任务转OTX，平衡一部分工作量） |  | 低 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
2 | 组员项目release前的规范流程与注意事项 |  | Medium | 内部成员与干系人做好相关的更改流程confirm操作 |  | Open | 2021-05-28
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
杨志恒 |  | 2020-07-02 |  |  | high | Planned last day 28-May
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A38: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A43: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W14
Project Weekly Status Report (01Apr,2021 - 31May,2021)
Author | hubo |  | Reviewed by | PM |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-06-05
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 81% | 82% | -1% | 84% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 73% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 21% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-05-31 | 2021-06-04 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-05-31 | 2021-06-04 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-05-31 | 2021-06-04 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-05-31 | 2021-06-04 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-06-07 | 2021-06-11 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-06-07 | 2021-06-11 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-06-07 | 2021-06-11 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-06-07 | 2021-06-11 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月、六月同步进行的project相对集中。部分项目时间需错峰调整 |  | Medium | 与客户及内部同事沟通，部分能错峰的，做好排期优化调整 |  | Open | 2021-05-28
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。（OTX部分交接任务分担及ICCM部分任务转OTX，平衡一部分工作量） |  | 低 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
2 | 组员项目release前的规范流程与注意事项 |  | Medium | 内部成员与干系人做好相关的更改流程confirm操作 |  | Open | 2021-05-28
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A38: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A43: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W15
Project Weekly Status Report (7June,2021 - 11June,2021)
Author | hubo |  | Reviewed by | PM |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-06-11
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 84% | 84% | 0% | 86% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 75% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 23% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-06-07 | 2021-06-11 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-06-07 | 2021-06-11 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-06-07 | 2021-06-11 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-06-07 | 2021-06-11 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-06-14 | 2021-06-18 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-06-14 | 2021-06-18 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-06-14 | 2021-06-18 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-06-14 | 2021-06-18 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月、六月同步进行的project相对集中。部分项目时间需错峰调整 |  | Medium | 与客户及内部同事沟通，部分能错峰的，做好排期优化调整 |  | Open | 2021-05-28
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 这两个月ICCM和OTX工作量不平衡，ICCM明显多于OTX。ICCM组员工作量太满。（OTX部分交接任务分担及ICCM部分任务转OTX，平衡一部分工作量） |  | 低 | 调配更多OTX人员学习ICCM技术，支援目前ICCM项目进度，主要先帮忙做一些testing support和机械性工作。新进人员计划优先安排给ICCM team。 | Closed | 项目经理和leader | 2021-04-30
2 | 组员项目release前的规范流程与注意事项 |  | Medium | 内部成员与干系人做好相关的更改流程confirm操作 |  | Open | 2021-05-28
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A38: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A43: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W16
Project Weekly Status Report (14June,2021 - 18June,2021)
Author | hubo |  | Reviewed by | PM |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-06-18
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 86% | 86% | 0% | 88% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 77% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 25% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-06-14 | 2021-06-18 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-06-14 | 2021-06-18 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-06-14 | 2021-06-18 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-06-14 | 2021-06-18 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-06-21 | 2021-06-25 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-06-21 | 2021-06-25 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-06-21 | 2021-06-25 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-06-21 | 2021-06-25 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-04-30
2 | 五月、六月同步进行的project相对集中。部分项目时间需错峰调整 |  | Medium | 与客户及内部同事沟通，部分能错峰的，做好排期优化调整。 |  | Open | 2021-05-28
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 组员项目release前的规范流程与注意事项 |  | Medium | 内部成员与干系人做好相关的更改流程confirm操作 |  | Closed | 2021-05-28
2 | 客户方组织结构调整，新合同确定下来后，内部也会相应的调整。并提前做好相应的人员补充准备。 |  | Medium | 客户内部部门会有相应的调整，届时与我们对接项目的POD LEAD负债人相应会有调整。另，OTX与ICCM CS会独立出来 |  | Open
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A38: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A43: caidehui: 请填入项目目前主要的问题，已解决的问题请移出

## W17
Project Weekly Status Report (21June,2021 - 25June,2021)
Author | hubo |  | Reviewed by | PM |  | Confirmed by | Wesley
Project ID |  |  | Project Name | ICCM & OTX 项目机会 |  | Report Date | 2021-06-25
Project Overall Status
Measurement | Planned of this week | Actual of this week | Deviation of this week | Planed of next week | Achievement compare to last week | Cause Analysis of Deviation& Response measures (Mandtory field when 'Deviation of this week' or 'Achievement compare to last week' is red)
Schedule | 88% | 88% | 0% | 90% | 2%
Effort | 100 | 100 | 0 | 100 | NA
Phases/ Milestones
Phases/ Milestones | Completion % | Status | Planned End Date | Due Date | Reasons of Delay
活动总量 （请隐藏，用于Excel条件格式计算） | 100% | Green
Phase 1 ICCM tasks | 100% | Green | 2020-09-15 | 2020-09-15
Phase 1 OTX tasks | 100% | Green | 2020-09-30 | 2020-09-30
Phase 2 ICCM tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 2 OTX tasks | 100% | Green | 2020-11-30 | 2020-11-30
Phase 3 ICCM tasks | 100% | Green | 2021-03-30
Phase 3 OTX tasks | 100% | Green | 2021-03-30
Phase 4 ICCM & OTX tasks | 100% | Green | 2021-03-30
Phase 5 ICCM & OTX tasks | 80% | Yellow | 2021-07-15
Phase 6 ICCM & OTX tasks | 28% | Yellow | 2021-09-15
Post Implementation Support | 0% | Green | 2021-09-15 |  | 预期6月份接完所有任务，8月或9月完成所有交付
Tasks of This Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Reasons for Delay/ Remarks
`1 | ICCM project development Phase 4 | 2021-06-21 | 2021-06-25 | 100% | Alex H P XIE, June
2 | OTX project development Phase 4 | 2021-06-21 | 2021-06-25 | 100% | Min Z QIU, Kashing
3 | ICCM project development Phase 5 SIT/UAT/Release | 2021-06-21 | 2021-06-25 | 100% | Alex H P XIE, June
4 | OTX project development Phase 5 SIT/UAT/Release | 2021-06-21 | 2021-06-25 | 100% | Min Z QIU, Kashing
Plan of Next Week
WBS No. | Task Name | Planned Start | Planned End | Completion（%） | Owner | Remarks
`1 | ICCM project Phase 5 Dev/SIT/UAT | 2021-06-28 | 2021-07-02 | 100% | Alex H P XIE, June
2 | OTX project Phase 5 Dev/SIT/UAT | 2021-06-28 | 2021-07-02 | 100% | Min Z QIU, Kashing
3 | ICCM & OTX project development Phase 4 UAT/Release | 2021-06-28 | 2021-07-02 | 100% | Alex H P XIE,Min Z QIU, Kashing
4 | ICCM & OTX Phase 6 project development | 2021-06-28 | 2021-07-02 | 100% | Alex H P XIE,Min Z QIU, Kashing
Risks
Risk No. | Risk Description |  | Risk Priority Number | Solutions | Project timeline impact | Current Status | Expected Mitigation Date
1 | 不少项目由于提需求方的各种原因有所延期，影响部分项目交付进度 |  | Medium | 1. 跟客户沟通具体情况，调整部分项目分值 2.主动定期催促对方进度和要求提供确切期限，多次无反馈直接把该项目设为暂停状态。 |  | Closed | 2021-07-15
2 | 五月、六月同步进行的project相对集中。部分项目时间需错峰调整 |  | Medium | 与客户及内部同事沟通，部分能错峰的，做好排期优化调整。 |  | Pending | 2021-05-28
Issues
Issue No. | Issue Description |  | Impact | Solutions | Current Status | Owner | Planned Close Date
1 | 客户方组织结构调整，新合同确定下来后，内部也会相应的调整。并提前做好相应的人员补充准备。 |  | Medium | 客户内部部门会有相应的调整，届时与我们对接项目的POD LEAD负债人相应会有调整。另，OTX与ICCM CS会独立出来。ICCM&OTX新任务项目计划拆分 |  | Open
2 | CMMI评估支撑 |  | Medium | 汇丰ICCM&OTX配合，CMMI项目评审答疑支持等工作 |  | Open
Resource Plan
Resource Name | Plan onboarding date | Actual onboarding date | Plan Release Date | Actual Rlease date | Retention risk | Remark
曾泽理 |  | 2021-03-22 |  |  | low
梁世杰 |  | 2021-03-22 |  |  | low
胡霞波 |  | 2021-03-22 |  |  | low
黄颖钧 |  | 2021-03-22 |  |  | low
岳俊瀚 |  | 2020-06-22 |  |  | low
陈永 |  | 2020-06-23 |  |  | low
何宇 |  | 2020-06-24 |  |  | low
刘清 |  | 2020-06-25 |  |  | low
李升球 |  | 2020-06-26 |  |  | low
梁志豪 |  | 2020-06-27 |  |  | medium
邱志民 |  | 2020-06-28 |  |  | low
王冠雄 |  | 2020-06-29 |  |  | low
谢昊鹏 |  | 2020-06-30 |  |  | low
许少斌 |  | 2020-07-01 |  |  | low
马晓弟 |  | 2020-07-03 |  |  | low
林世兴 |  | 2020-07-04 |  |  | low
韦嘉诚 |  | 2020-09-05 |  |  | low
张颖 |  | 2021-03-29 |  |  | low
Remarks:
1 WSR based on data
2 WSR data are from WBS, timesheet, Risk&issue management form, metrics form, or other related documents.
3 The task status is either 0% or 100% . If the task takes over a week, pls divide into sub tasks. The phase/milestone progress depends on the number of completed tasks in it or ETC（EVM）.
4 Risk Priority Number is from Risk&issue management form. RPN>=75 Very High;45<=RPN<75 High;6<=RPN<40 Medium;RPN<6 low.
Note on B9: Catherine: Completion% calculated by the number of task or ETC
Note on A22: Catherine: From Timesheet/WBS
Note on E22: Catherine: Only 0% or 100% are allowed. If the task takes over a week, pls divide into sub tasks
Note on A28: Catherine: From Timesheet/WBS
Note on E28: Catherine:
Note on A33: caidehui: 请填入目前需要解决的关键风险，已经解决的风险请不要移出。
Note on A34: Catherine: From Risk& Issue Manangement form
Note on D34: Catherine: >=75 Very High; 45<=RPN<75 High; 6<=RPN<40 Medium; <6 low
Note on A38: caidehui: 请填入项目目前主要的问题，已解决的问题请移出
Note on A43: caidehui: 请填入项目目前主要的问题，已解决的问题请移出